## Project Timeline
Activity | 2025-11-28 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21
Initial Repo Setup & Structure
.gitignore & Environment Config
Project Plan
Documentation
ETL Pipeline
Repo Layer (API Fetch)
Service Logic (Stress Index)
Database Adapter
Security: SQL Injection fix
Logging configuration
Dashboard UI & Routing
UKHSA Risk Logic Enhancement
Admin Panel (CRUD functionality)
TDD Cycle
Refactoring
Final documentation (Readme)
Report draft
Final report polish and upload
Note: between 29th November and 9th December, resources were re-allocated towards group project deliverables.
Note: between 9th and 11th December, I was working on external job assessments and interviews.

## Kanbak Board
Activity | Status
[Setup] Repo initialisation | Done
[Backend] ETL pipeliline for hospital capacity CSV | Done
[QA/Test] Unit Test: Service Layer Logic | Done
[Backend] Repo layer (CDC API integration) | Done
[Logic] Service Layer Implementation | Done
[QA/Test] Database Test: Database Adapter | Done
[DB] Database Adapter (SQLite Save/Load] | Done
[Ops] Centralised logging configuration | Done
[Security] SQL Injection Prevention: Parametrised Queries | Done
[Entrypoint] Implement entrypoint | Done
[QA/Test] UI Tests and logic | Done
[UI] Implement dashboard | Done
[UI] Refactor dashboard | Done
[QA/Test] Test for app routing | Done
[UI] Implement dashboard with routing and admin panel | Done
[QA/Test] TDD Cycle: Risk Logic enhancements | Done
[Logic] UKHSA risk tier logic (1:15 ratio, low/mod/high/crit) | Done
[QA/Test] Testing enhancements | Done
[QA/Test] App initialisation | Done
[UI] Complete dashboard logic, KPIs, etc | Done
[Docs] README documentation and installation guide | Done
[Docs] Generating UML and ER Diagrams | In Progress
[Feature] User authentication | Backlog
[Feature] Data export | Done
[DevOps] Docker containerisation | Backlog
[Feature] R-number estimation | Backlog
[UI] Interactive chloropleth map | Backlog
[Notification] Email alerts for critical states | Backlog

## User stories
ID | Role | User Story | Description | Acceptance Criteria | Priority | Status
US-01 | Researcher | Filter the dashboard by State(s) | I can isolate regional outbreaks without visual clutter from all 50 states. | Sidebar "Select States" widget updates the charts instantly. | Must | Done
US-02 | Researcher | View a Healthcare Stress Index | I can assess the true hospital burden (Deaths vs Beds), not just raw counts. | System calculates (Deaths * 15) / Beds and shows percentage. | Must | Done
US-03 | Researcher | Filter analysis by Date Range | I can focus on specific flu seasons or exclude historical data. | Date Slider in sidebar updates the X-axis range. | Should | Done
US-04 | Admin | Manually Updatehospital bed capacity | I can ensure the stress calculation is accurate when hospitals expand/close wings. | Admin Form submits value; Database & CSV update immediately. | Must | Done
US-05 | Admin | Trigger a manual Data Sync | I can fetch the latest provisional CDC data without restarting the server. | "Trigger Sync" button in Admin Panel refreshes the database. | Must | Done
US-06 | User | See "Traffic Light" risk indicators | I can instantly spot "Critical" states (Red) vs "Safe" states (Green). | States with Stress Index > 70% are highlighted Red. | Should | Done
US-07 | System | Cache data in a local Database | The tool works offline or when the CDC API is down. | Dashboard loads from health_dashboard.db on startup. | Must | Done
US-08 | Manager | View aggregated KPIs (e.g., Peak Stress) | I can get a high-level summary without interpreting complex graphs. | Metric cards at the top display Max Stress & Total Deaths. | Should | Done
US-09 | Dev/Admin | View system Logs | I can debug issues if the data fails to load. | app.log file records timestamps of all API calls and errors. | Could | Done
US-10 | Researcher | Compare two states side-by-side | I can benchmark how different regions handled the same outbreak. | Chart allows overlaying State A vs State B in different colors. | Could | Backlog
US-11 | Analyst | Export the filtered data to CSV | I can perform custom pivot analysis in Excel. | "Download Data" button appears below the dataframe. | Could | Done
US-12 | User | View a Geospatial Map(Heatmap) | I can see the geographic spread of the virus across the US. | US Map visualisation colors states by Stress Index. | Could | Backlog
US-13 | Admin | Log in with a secure password | I can prevent unauthorised users from changing hospital data. | Login screen gates access to the Admin Panel. | Won't | Backlog
US-14 | Auditor | View an Audit Trail of changes | I can see who changed the hospital bed capacity and when. | Database table audit_logrecords User ID and Timestamp of updates. | Won't | Backlog
US-15 | Researcher | Calculate the R-Number(Infection Rate) | I can predict if the outbreak is growing or shrinking. | Algorithm estimates R based on week-over-week death growth. | Could | Backlog
US-16 | User | Receive Email Alerts | I know immediately when a state hits "Critical" status. | SMTP service sends email when Risk Level = Critical. | Could | Backlog
US-17 | Researcher | Correlate with Weather Data | I can see if temperature and other weather data (eg wind) affect flu spikes. | System ingests API data from OpenWeatherMap. | Won't | Backlog
US-18 | System | Archive old data automatically | The database doesn't become too slow over years of usage. | Cron job moves data older than 5 years to archive.db. | Won't | Backlog

## Functional Requirements
ID | Requirement Statement | Priority (MoSCoW) | Acceptance Criteria | Implemented?
FR-01 | The System shall connect to the CDC Open Data API (r8kw-7aab) via HTTPS GET requests to retrieve provisional mortality data. | MUST | Returns JSON payload with status code 200; Handles 404/500 errors gracefully. | Yes
FR-02 | The System shall persist retrieved data into a local SQLite relational database (health_dashboard.db) to ensure data availability during network outages. | MUST | Data persists across application restarts; load_data() retrieves rows when offline. | Yes
FR-03 | The System shall implement an Extraction-Transformation-Loading (ETL) pipeline to merge API JSON data with local CSV Capacity data based on the state key. | MUST | Joined DataFrame contains both flu_deaths and ICU_Beds columns. | Yes
FR-04 | The System shall calculate the Healthcare Stress Indexusing the algorithm: Index = \frac{FluDeaths \times 15}{ICU\_Beds} \times 100. | MUST | Unit test verifies that 10 deaths / 50 beds returns exactly 300.0. | Yes
FR-05 | The System shall provide a web-based Admin Interfacethat allows users to Update (CRUD) the Total_Hospital_Beds and ICU_Beds for any given state. | MUST | Submitting the form updates the specific row in the SQLite database immediately. | Yes
FR-06 | The System shall allow users to select one or multiple states from a sidebar widget to filter the visualisations dynamically. | MUST | Selecting "Texas" hides all other state data from the charts. | Yes
FR-07 | The System shall visualise mortality and stress trends over time using an interactive Line Chart. | SHOULD | Chart supports hover-over tooltips displaying exact values for specific dates. | Yes
FR-08 | The System shall categorise states into Risk Tiers: Low (<10%), Moderate (10-40%), High (40-70%), and Critical (>70%). | SHOULD | UI renders "Critical" text in Red and "Low" text in Green. | Yes
FR-09 | The System shall allow filtering the analysis period via a Date Range Slider widget. | SHOULD | Adjusting the slider excludes records outside the selected start/end dates. | Yes
FR-10 | The System shall display aggregated Key Performance Indicators (KPIs) (Total Deaths, Peak Stress) at the top of the dashboard. | SHOULD | KPI numbers update dynamically based on the active State/Date filters. | Yes
FR-11 | The System shall provide a "Trigger Sync" mechanism to force a fresh data fetch from the CDC API on demand. | COULD | Clicking the button executes repo.fetch_data()and reloads the page. | Yes
FR-12 | The System shall generate a downloadable CSV exportof the currently filtered dataset. | COULD | Clicking "Download" prompts the browser to save filtered_data.csv. | No
FR-13 | The System shall visualise the geographic distribution of stress using a Choropleth Map of the USA. | COULD | Map is color-coded by Stress Index; Hovering shows state details. | No
FR-14 | The System shall authenticate administrators via a Login Screen before granting access to the CRUD panel. | WON'T | Users cannot access /adminwithout a valid session token. | No
FR-15 | The System shall validate input data on the Admin Panel to prevent negative numbers for bed capacity. | WON'T | Entering "-50" displays a validation error message; Form is not submitted. | No
FR-16 | The System shall calculate the Reproduction Rate of the infection based on weekly growth factors. | WON'T | Dashboard displays an estimated R number alongside the Stress Index. | No
FR-17 | The System shall send SMTP Email Alerts to a configured address when a state enters "Critical" risk level. | WON'T | Email is received within 5 minutes of the data sync detecting the condition. | No
FR-18 | The System shall maintain an Audit Log (audit_trail.log) recording the timestamp and user ID of every manual data override. | WON'T | Log file contains entries like [2024-12-21] Admin updated TX beds to 500. | No

## Non Functional Requirements
Category | ID | Requirement | Priority | Metric / Constraint | Implemented?
Functionality | NFR-01 | Accuracy | Must | Stress Index calculations must be precise to 2 decimal places to prevent rounding errors in critical reporting. | Yes
Functionality | NFR-02 | Data Freshness | Should | When "Sync" is triggered, data must be no older than the latest available CDC dataset (typically < 1 week lag). | Yes
Usability | NFR-03 | Learnability | Should | A first-time Researcher must be able to filter by State and view the chart within 10 seconds without reading documentation. | Yes
Usability | NFR-04 | Error Feedback | Must | System must display user-friendly warnings (e.g., "Using Offline Cache") instead of raw Python tracebacks/stack traces. | Yes
Usability | NFR-05 | Accessibility | Could | The dashboard UI must comply with WCAG 2.1 AAstandards (e.g., high contrast for colorblind users). | No
Usability | NFR-06 | Localisation | Won't | The interface should support switching languages (e.g., English/Spanish) for diverse public health teams. | No
Reliability | NFR-07 | Fault Tolerance | Must | System must default to local SQLite cache if the CDC API returns a 500/503 or 404 error. | Yes
Reliability | NFR-08 | Data Persistence | Must | Manual updates to Hospital Capacity must persist across application restarts (ACID compliance via SQLite). | Yes
Reliability | NFR-09 | Recoverability | Could | System should perform automated daily backups of the health_dashboard.db file to a separate directory. | No
Performance | NFR-10 | Latency (Render) | Should | Dashboard must render the visualisations for all 50 states in under 3 seconds on standard hardware. | Yes
Performance | NFR-11 | Latency (API) | Should | API data fetch operations should time out after 15 seconds to prevent the UI from freezing indefinitely. | Yes
Performance | NFR-12 | Scalability | Could | The architecture must support containerisation (Docker) to handle 1,000+ concurrent users in a cloud environment. | No
Performance | NFR-13 | Capacity | Must | Database must store at least 5 years of weekly historical data without query performance degrading >50%. | Yes
Supportability | NFR-14 | Modularity | Must | Application must adhere to Service-Repository Pattern; UI code must not import requests or SQL libraries directly. | Yes
Supportability | NFR-15 | Portability | Must | Application must be platform-agnostic, running on Windows, macOS, and Linux (requires only Python 3.9+). | Yes
Supportability | NFR-16 | Maintainability | Could | Codebase should maintain a Cyclomatic Complexity score under 10 (checked via flake8 or radon). | No
Security | NFR-17 | Input Hygiene | Must | All Database interactions must use Parameter Binding (e.g., ?) to prevent SQL Injection attacks. | Yes
Security | NFR-18 | Data Encryption | Won't | Sensitive hospital data (Capacity) should be encrypted at rest (AES-256) within the SQLite database. | No

## Test Plan
Seq | Date | Feature / Component | Test Function Name | Test Type | Scenario / Logic Tested | TDD State
1 | 2025-12-12 | Service Layer | test_stress_index_calculation | Unit | Logic: Verify Stress Index Formula (Deaths * 15) / Beds * 100. | RED (Fail)
Input: 10 Deaths, 50 Beds.
Expected: 300.0.
1.1 | 2025-12-14 | Service Layer | test_stress_index_calculation | Unit | Implementation of _calculate_stress method to pass the test. | GREEN (Pass)
2 | 2025-12-14 | Database Adapter | test_save_and_load_data_integrity | Integration | Logic: Verify Data Persistence. | RED (Fail)
Input: DataFrame with 'Alaska', 'California'.
Expected: load_data() returns 2 rows; 'Alaska' exists.
2.1 | 2025-12-16 | Database Adapter | test_save_and_load_data_integrity | Integration | Implementation of sqlite3connection and INSERT queries. | GREEN (Pass)
3 | 2025-12-17 | UI Layer | test_app_initialization | UI Unit | Logic: App Startup & Mocking. | RED (Fail)
Input: Mock setup_logger and st.sidebar.
Expected: main() is callable without crashing.
3.1 | 2025-12-17 | UI Layer | test_app_initialization | UI Unit | Implementation of main.py entry point and routing. | GREEN (Pass)
4 | 2025-12-17 | Risk Logic (Enhancement) | test_service_logic_with_ukhsa_... | Unit | Logic: UKHSA Risk Thresholds. | RED (Fail)
Input: 6 Deaths, 100 Beds (Stress 90%).
Expected: Label "Critical" (>70%).
4.1 | 2025-12-18 | Risk Logic (Enhancement) | test_service_logic_with_ukhsa_... | Unit | Implementation of _categorise_riskwith UKHSA thresholds. | GREEN (Pass)
5 | 2025-12-18 | UI Components | test_ui_renders_risk_indicators | UI Unit | Logic: Visual Feedback. | RED (Fail)
Input: Risk Level 'Critical'.
Expected: Color code 'darkred'.
5.1 | 2025-12-18 | UI Components | test_ui_renders_risk_indicators | UI Unit | Implementation of get_risk_colorhelper method in dashboard.py. | GREEN (Pass)
6 | 2025-12-18 | UI Logging | test_ui_initialisation_logs_startup | UI Unit | Logic: Startup Logging. | RED (Fail)
Expected: Log contains "User session started".
6.1 | 2025-12-20 | UI Logging | test_ui_initialisation_logs_startup | UI Unit | REFACTOR: Updated test assertion to match actual log message "FluDashboardUI Initialised". | GREEN (Pass)
7 | 2025-12-21 | Resilience | test_get_dashboard_data_api_failure_fallback | Unit | Logic: Fault Tolerance. | GREEN (Regression)
Input: API returns [] (503 Error).
Expected:Service calls db.load_data()instead of crashing.
8 | Planned | Security (Auth) | test_admin_login_invalid_credentials | Unit | Logic: Authentication. | Not Implemented
Input: Username "admin", Password "wrongpass".
Expected: System returns 401 Unauthorised; Access denied.
9 | Planned | Security (Auth) | test_access_control_admin_route | Integration | Logic: RBAC (Role Based Access Control). | Not Implemented
Input: Unauthenticated user tries to access /admin.
Expected: Redirect to /login page.
10 | Planned | Data Export | test_download_csv_content | Integration | Logic: Data Serialisation. | Not Implemented
Input: Filter set to "Texas" only.
Expected: Generated CSV contains only Texas rows; Content-Type is text/csv.
11 | Planned | Input Validation | test_update_beds_negative_value | Unit | Logic: Data Integrity. | Not Implemented
Input: Admin submits "-50" Beds.
Expected: ValueErrorraised; Database is notupdated.
12 | Planned | Performance | test_stress_load_large_dataset | Performance | Logic: Scalability (NFR-13). | Not Implemented
Input: Mock DB with 50,000 historical records.
Expected:get_dashboard_data()returns in < 3.0 seconds.
13 | Planned | Visualisation | test_heatmap_geojson_mapping | UI Unit | Logic: Geospatial Mapping. | Not Implemented
Input: State "California" with Stress 90%.
Expected: Map component receives correct lat/long and color "Red".
14 | Planned | Notifications | test_email_alert_trigger | Integration | Logic: SMTP Alerting. | Not Implemented
Input: Risk Level hits "Critical".
Expected:smtplib.sendmail is called with correct recipient address.